## Work programme
A - PREPARATORY ACTIONS
A1 Site visits
A2 Desk research
A3 Online nominations
A4 Assessment process
B - IMPLEMENTATION
B1 Community groups engagement
B2 Station staff engagement
B3 Schools programme
B4 Community events
B5 Legal procedures for solar energy
B6 Share offer for solar
B7 Preparatory work on site
B8 Construction on site
B9 Garden maintenance
B10 Internship and work experience programme
B11 Community champions
B12 Accredited training
B13 Corporate volunteering
B14 Overground in Bloom competition
B15 Exit and legacy planning
C - MONITORING
C1 Evaluation
C2 Surveys
C3 Evaluation report
D - COMMUNICATION AND DISSEMINATION
D1 Internal project communications
D2 Online presence
D3 Engagement with and dissemination to all stakeholders
D4 Project marketing materials
D5 Film
E - PROJECT MANAGEMENT
E1 Reporting
E2 Progress meetings

## Risk log
WP | Risk or Issue | Probability | Impact | Score | Mitigating actions | Status
A1 | Unable to obtain sufficient or accurate information | 2 | 4 | 8 | Provide guidance to staff and volunteers before site visit. Allow for follow up site visits in timescale.
A1 | Many sites to visit, not enough staff capacity | 4 | 4 | 16 | Volunteers to do initial scout to highlight quick wins and eliminate non-viable stations, where possible
A2 | Key information not available | 1 | 4 | 4 | Use internal GIS Team. Liaise with project partners and networks.
A3 | Low level of online nominations | 3 | 3 | 9 | Monitor. Publicise widely.
A4 | Lack of suitable stations (under 50 target) | 1 | 5 | 5 | Continually monitor. Define suitable assessment criteria. Look at stations which could have smaller projects
A4 | Conditions at station change post site visit | 2 | 3 | 6 | Monitor. Ensure designs remain flexible. Communicate with station staff
B1 | Lack of interest from community groups | 3 | 4 | 12 | Build relationships with key partners, local groups from the start. Where there is low community interest ensure that plants are low maintenance or station staff to manage. Ensure as many local groups as possible are engaged. Look at pop-up events to generate more interest
B1 | Community groups not interested in gardening | 3 | 3 | 9 | Station will focus on low maintenance plants
B1 | Conflicts between groups | 1 | 3 | 3 | Where necessary, define roles and responsibilities with memo of understanding. Address any issues early on through clear communications and meetings
B1 | High expectations from group | 2 | 1 | 2 | Ensure that group are clear about what can and cannot be done, without diffusing their enthusiasm, make sure that group are aware that any suggestions need TfL approval
B1 | Problems collating details of all local community groups | 1 | 2 | 2 | GIS team to create mapping system of groups, volunteers to collate data. Contacts spreadsheet used to collate all email addresses, contacts etc. Comms team to collate tweets
B2 | Difficulty in contacting station managers | 2 | 3 | 6 | Get contact details from Lorel, get updated contact from ground staff if changed
B2 | Lack of cooperation from station staff | 2 | 2 | 4 | Get TfL and Lorel to communicate project to their staff. Not all staff are going to be interested, focus on staff who are
B3 | Unable to target 50 schools | 3 | 4 | 12 | Focus on schools we already have a relationship and ones next to stations. Make links with schools officer of borough
B3 | Lack of interest from schools in school workshops | 3 | 4 | 12 | Monitor, could the programme be tailored or improved
B3 | Lack of interest in schools of site visits | 3 | 4 | 12 | Monitor, don't include the site visit
B3 | Unsuitable local stations for school visits | 2 | 2 | 4 | Log most suitable stations for visits with at least one per borough, where possible. Their local station won't necessarily be the one they visit
B3 | Target of 1500 kids benefitting from school sessions not met | 3 | 4 | 12 | Monitor
B3 | Unable to deliver one school session per garden due to lack of capacity, time | 2 | 3 | 6 | Monitor, review strategy of delivery
B3 | TfL not willing for school visits to stations | 3 | 2 | 6 | Plan in school workshops
B3 | Schools not interested in taking out children from school in colder seasons | 2 | 2 | 4 | Plan project accordingly
B4 | TfL not allowing family fun day to happen | 2 | 3 | 6 | Change event plan to parks or green spaces near/next to station, inform funder that target may not be met
B4 | TfL slow to approve family fun day | 4 | 3 | 12 | Give TfL plenty of time to approve, have back-up plan (see above)
B4 | Target of family fun day benefitting 1000 people not met | 2 | 3 | 6 | Promote widely, get additional staff to support. Spread event out so it's not happening at one site. Plenty of prep time to organise. Also promote through schools, existing community groups etc. Make the event exciting, give people incentive to attend. Develop comm strategy for promotion
B4 | Target of 3 ad-hoc educational events at each site (11,250 people benefitting) not met | 2 | 3 | 6 | Monitor
B4 | Pop-up events are not well attended | 2 | 2 | 4 | Events will take place at busy stations such as interchange, flagships at peak eve times
B5 | Unable to agree lease for solar enegry |  |  |  | Repower
B5 | Unable to obtain planning permission for solar energy |  |  |  | Repower
B6 | Difficulty in adminstrating share offer |  |  |  | Repower
B6 | Lack of buyers for share offer |  |  |  | Repower
B7 | Unable to obtain plants from Chelsea Flower Reuse scheme | 2 | 1 | 2 | Plan what we need and where it could go in advance, look at the procedure for getting involved in scheme in advance
B7 | Unable to take advantage of free plant/tree schemes | 2 | 1 | 2 | As above
B7 | No-where to store trees/plants | 2 | 1 | 2 | Explore possibility of creating temporary nursery at one of the stations, buy trees/plants as close to deadline as possible
B7 | TfL only allow their own contactor to do the work | 3 | 3 | 9 | Make sure this is defined early in project
B7 | TfL contractors are more expensive | 3 | 3 | 9 | Revise the FYP and project delivery, see if TfL can be more flexible
B9 | No access to water | 2 | 4 | 8 | Ensure this is picked up during initial site visits, arrange for water butts, water harvesting, solar irrigation or tap to be installed
B7 | Also see Landscape RA
B8 | See Landscape RA
B9 | Volunteers have problems accessing garden | 1 | 4 | 4 | Ensure station staff are aware of the project, they should have a sign-in system in place. Create a welcome pack so volunteers are aware of the procedure
B9 | Volunteers do not follow safety guidelines whilst working at the station | 3 | 4 | 12 | Provide handbook to volunteers. Check in with station staff regularly.
B9 | Gardens not maintained to adequate standards, affecting the reputation of the project | 3 | 4 | 12 | Arrange regular Green Team maintenance. Provide support to community groups. Set-up training sessions or Community Gardening-led sessions
B9 | Green Team are unable to cover east and south London area | 5 | 2 | 10 | Community Gardeners to cover areas that Green Team cannot manage, for larger projects look at contractors
| No access and storage of tools | 3 | 3 | 9 | Where possible arrange for each project to have basic tools with access, ensure that staff, groups are aware of where these are kept
B9 | Groups not completing sign-in sheets | 3 | 4 | 12 | Ensure memo of understanding states that quarterly data collection is required, communicate which forms need to be completed. Keep process simple
B9 | Groups not promoting their projects on Project Dirt | 2 | 2 | 4 | See above, encourage groups to post blogs, events themselves
B10 | Target of 10 youth internships not met | 2 | 3 | 6 | Repower
B11 | Target of 150 Community Champions trained and supported not met | 2 | 3 | 6 | Monitor, ensure strategy of recruiting Champions is part of the project before delivery
B11 | Champions don't commit to project in long-term | 4 | 3 | 12 | Ensure enough active Champions to support project, create strategy to keep Champions enagaged in project, incentives
B12 | Unable to gain accreditation for training qualification | 1 | 3 | 3 | Early engagement with the accreditation body will ensure that the modules comply with all requirements, this will be led by Community Gardeners so needs to be communicated with them
B12 | Target of 100 people to gain accreditation not met | 2 | 2 | 4 | Monitor
B13 | Target of 750 corporate volunteers across 25 sites (total 5600 volunteer hours) not met | 2 | 2 | 4 | Monitor, send all opportunities to Ben Coles as early as possible
B14 | Target of 25 Overground in Bloom entries not met | 3 | 2 | 6 | Monitor, look at whether we can have any early entries for 2015, communicate with station staff to ensure that their station is entered
B15 | Garden is not maintained | 3 | 4 | 12 | Capacity building programme for community. Schedule in Green Team maintenance. Gardens which aren't successful can be taken out by request of TfL
B15 | Insufficient funds raised from solar energy to support garden |  |  |  | Repower
C1 | Groups aren't collecting data of gardening sessions | 3 | 4 | 12 | Ensure memo of understanding states that quarterly data collection is required, communicate which forms need to be completed. Keep process simple. Ensure that data collection is robust and monitor
C2 | Lack of reliable data | 2 | 3 | 6 | As above, ensure base-line data is collected, monitor
D1 | Staff turnover impacting on project communications | 2 | 2 | 4 | Ensure minutes are taken at meetings, and that project database is kept up to date
D1 | Poor communication | 2 | 2 | 4 | Ensure regular meetings, copy relevant people into emails, used share drive
D2 | Low number of hits to website and social media | 2 | 1 | 2 | Monitor, Comms to be more active with web updating, tweets, Facebook etc.
D2 | No Energy Garden presence on partner website | 2 | 1 | 2 | Make Repower aware of this
D2 | No management of Energy Garden website | 2 | 1 | 2 | Clarify which partner is responsible and give task to staff
D3 | Disagreements between stakeholders on project | 2 | 2 | 4 | Ensure clear communication throughout. Manage stakeholder expectations from the start
D3 | Information not relevant to stakeholders | 2 | 1 | 2 | Tailor information to relevant stakeholders, internal agreements about what to disseminate
D4 | Project does not have strong brand or messaging | 1 | 4 | 4 | Work with Comms team
D4 | TfL slow to approve branding | 5 | 3 | 15 | Get system in place to ensure quicker sign-off and to simplfy process
D4 | Designs delayed due to internal designers work load | 2 | 2 | 4 | Give designer at least 3 weeks window for design
D4 | Welcome pack is not relevant to community groups | 2 | 2 | 4 | Ensure content is relevant and keep easy to use as a PDF format
D5 | Unable to deliver the film internally | 3 | 1 | 3 | Get contacts and costings for external contractors, and adjust the FYP
D5 | Unable to get required footage for film | 2 | 3 | 6 | Create film strategy with Comms
E1 | Partner takes too long to inc. their input into reports | 3 | 2 | 6 | Ensure that partners and staff are aware of report deadlines, send reminders
E1 | Poor data quality, completeness and consistency | 2 | 2 | 4 | Monitor incoming data, see C1
E2 | Lack of availability for project meetings | 2 | 2 | 4 | Schedule meetings in advance and make provision for tele- and video conferencing
E2 | See D1